### Detailed sample of REU program yearly to-do list

##### JANUARY

- Set up your website with program dates and application procedure

- Advertise your site: recruitment visits and talks, emails, flyers, etc.

- Start working on project topics and mentors

- Register and submit information for PI meeting

##### FEBRUARY

- Revise applications received

- Finalize projects and select mentors

- Talk to mentors about the program: dates, expectations, etc.

- Talk to program evaluator and set up data collection for evaluation

- Make travel arrangements for PI meeting

##### MARCH

- Close application and organize application information

- Send letters of acceptance/rejection

- Finalize student lineup (obtain proof of citizenship or perm residency)

- Start planning site activities (speakers, visits, trips, workshops, fun, etc.)

- Coordinate activities with other REU programs on campus (welcome ceremony)

- Finalize evaluation instruments (surveys, questionnaires, etc.)

- Attend PI meeting

##### APRIL

- Email students with general information (airport pickup, dress code,
payment schedule, dorm information, first day of work date, etc.)

- Make travel arrangements including pickup of students

- Make housing and meal arrangements

- Process student IDs

- Set up payment procedure and schedule

- Finalize site program

##### MAY

- Set up labs (computers, access, any other hardware/software, etc.)

- Set up email accounts

- Pick up students from airport and take them to the dorms

- Take students to buy stuff for the dorms (grocery, etc.)

- Tour of campus

- Meet their mentors

- Get first stipend

- Welcome ceremony and Intro session about the program (activities, program, expectations, etc.)

** List of example activities: **

Talk about graduate school and how to find funding for it

GRE workshop

How to prepare a good fellowship application

Visits to sites/places of interest and fun and group building activities

Technical talks from invited faculty

How to write a good research paper

How to do and present a good poster

##### JUNE

- Research starts

- Weekly surveys for program evaluation and weekly meeting with students

- Second stipend

- Mid-program presentations

- Submission of draft of research paper or poster

##### JULY

- Weekly surveys for program evaluation

- Have weekly meetings with students

- Third stipend

- Rent car to take student to airport

- End of program presentations

- Submission of poster

- Submission of research paper

- Poster competition and closing ceremony

- Dorms checkout

- Students return to their homes

##### AUGUST

- Send post-program survey for program evaluation

- Collect information for renewal (statistics, publications, etc.)

- Prepare material for NSF annual report

- Work on research papers

##### SEPTEMBER

- Send all program evaluation material to program evaluator

- Obtain evaluator annual report

- Finalize research papers and submit for publication

- Solicit faculty interest for upcoming summer

##### OCTOBER

- Prepare and submit NSF annual report

- Open applications for upcoming summer program

##### NOVEMBER

- Start working on website for next year

##### DECEMBER

- Determine dates for next year

- Start advertisement process